SIGHT AFRICA · STRATEGIC OPERATING SYSTEM

SIGHT AGRI

Agricultural data & finance

Planned incorporation: 2034 · Execution starts 1 January 2027 · All amounts in FBU

## 1. What we expect from this entity

Combines DATA + PAY + COMPUTE for the continent's largest sector.

- Created in 2034, once the ecosystem demand for agricultural data & finance is proven by group volume.

- Serves group products first (internal customer), then external clients.

- Runs as a subsidiary with its own P&L, managing director and board.

## 2. Economic model

| Revenue line | Mechanism | Primary customer |
| --- | --- | --- |
| Internal services | Transfer pricing to SIGHT subsidiaries | Group products |
| External subscriptions | Recurring contracts, annual commitment | Banks, MNOs, corporates |
| Public-sector contracts | Tendered multi-year contracts | Governments, regulators |
| Usage-based fees | Per call / per unit consumed | Developers, partners |

## 3. Investment required

| Phase | Window | Capital needed | Main use |
| --- | --- | --- | --- |
| Study & design | 2033 | 60 M FBU | Feasibility, architecture, legal structure |
| Incorporation & MVP | 2034 | 450 M FBU | Entity setup, core team, first platform |
| Commercial ramp | 2035–2037 | 2 Mds FBU | Sales, certification, capacity |
| Consolidation | 2038+ | Self-funded | Reinvested cash flow |

## 4. Feasibility assessment

| Dimension | Assessment | Condition to satisfy |
| --- | --- | --- |
| Technical | Conditional on group maturity | Reuse of group platform (PAY · ID · CLOUD) |
| Regulatory | Sector-specific | Licences and certifications obtained before launch |
| Operational | Medium | Managing director recruited 12 months before launch |
| Financial | Funded by group cash flow + DFI debt | Group EBITDA positive at incorporation |
| Talent | Medium | Core team sourced from SIGHT ACADEMY alumni |

## 5. Decision rule

- Build only when internal demand already justifies at least 50% of the cost base.

- Wait if the market is not ready or a partner can serve it better for now.

- Outsource the first version, then internalise once volume is proven.

## 6. Risks & mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Premature launch | High | Gate on internal demand thresholds |
| Capital diversion from core | High | Hard cap on group funding per entity |
| Regulatory blockage | Medium | Pre-launch regulatory engagement |
| Talent scarcity | Medium | Academy pipeline + diaspora recruitment |