SIGHT AFRICA · STRATEGIC OPERATING SYSTEM

Priorities

What must be done, in which order, and by when.

Execution starts 1 January 2027 · 2026 is a preparation year outside the agenda · All amounts in FBU

## 0. Preparation year 2026 — before the agenda

2026 is used to prepare: legal structuring, group identity, capital, first hires and product readiness. Execution officially starts on 1 January 2027.

- Legal structuring of the group and the first subsidiaries.

- Group identity, brand system and single sign-on design.

- Capital: bootstrap discipline plus first angel commitments.

- First senior hires and product readiness reviews.

## 1. Yearly priorities (2027 → 2036)

2027 — Foundation & Brand

- Consolidate the four existing products under one SIGHT AFRICA group identity

- Stabilize BitLibera as a profitable BTC + mobile-money corridor

- Launch Africa Fintech Journal as a recognized regional publication

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 15M FBU ARR | 18 → 35 | BitLibera 2.0 (merchant pilot) · LEARN BTC certificate program v1 · AFJ weekly editorial |

2028 — Validation & Repeatability

- Open Bujumbura HQ + first satellite office in Kigali

- Reach product-market fit on Yepo for African SMEs accessing AI

- Launch SIGHT ID pilot for KYC across group products

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 60M FBU ARR | 35 → 80 | Yepo Business · SIGHT ID alpha · AFJ research reports |

2029 — Growth — Regional Footprint

- Cross-border payments live (BI ↔ RW ↔ DRC)

- Launch SIGHT ACADEMY as standalone institution

- First sovereign cloud zone (SIGHT CLOUD Lake Tanganyika)

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 220M FBU ARR | 80 → 220 | SIGHT PAY v1 · SIGHT ACADEMY cohort 1 · SIGHT CLOUD region 1 |

2030 — Platformization

- Open public APIs across PAY, ID, CLOUD

- Launch SIGHT CAPITAL fund I (450M FBU)

- Begin SIGHT LABS R&D center on applied AI and cryptography

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 600M FBU ARR | 220 → 480 | Developer portal · SIGHT CAPITAL fund I · SIGHT LABS |

2031 — National Milestone Consolidation

- Become the de-facto digital integration partner for Burundian state services

- Hit 5M end-users across the group

- Launch SIGHT SECURITY as standalone subsidiary

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 1,5 Md FBU ARR | 480 → 900 | SIGHT SECURITY SOC · Government services integration · AFJ data & research division |

2032 — Regional Expansion

- Enter Tanzania, Kenya, Uganda commercially

- Launch SIGHT DATA — analytics & data infrastructure

- Series B equivalent: 1,2 Md FBU growth round

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 3 Mds FBU ARR | 900 → 1,500 | SIGHT DATA · Multi-currency PAY corridors · Regional merchant network |

2033 — Infrastructure Leadership

- Position SIGHT CLOUD as preferred sovereign cloud for francophone Africa

- Launch SIGHT MARKET — cross-border digital commerce rails

- Establish governance & board for IPO-ready maturity

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 5,5 Mds FBU ARR | 1,500 → 2,400 | SIGHT MARKET · Sovereign cloud certification · Independent board |

2034 — AI & Compute Sovereignty

- Stand up African-owned GPU compute via SIGHT LABS

- Yepo becomes the default AI access layer for African SMEs

- Cross-listing readiness (NSE / regional exchanges)

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 9 Mds FBU ARR | 2,400 → 3,400 | SIGHT COMPUTE (GPU cloud) · Yepo Enterprise · Regulatory readiness pack |

2035 — Institutional Scale

- Operate in 7 countries; revenue diversification across 4 segments

- SIGHT CAPITAL fund II (1,8 Md FBU)

- Mature M&A engine for adjacent assets

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 13 Mds FBU ARR | 3,400 → 4,200 | Fund II · First two acquisitions (paytech, edtech) · Group ERP & financial backbone |

2036 — Foundational Infrastructure

- 9 countries, 18 Mds FBU ARR, recognized critical infrastructure operator

- Public listing or strategic long-term capital partnership

- Established African-owned alternative across PAY · ID · CLOUD · DATA · SECURITY

| Revenue target | Team | Key releases |
| --- | --- | --- |
| 18 Mds FBU ARR | 4,200 → 4,800 | IPO / strategic listing · 20-year national infrastructure compact (BI) · Pan-African API standard contributions |

## 2. Subsidiary launch order (2 to 3 per year)

| Rank | Entity | Role | Launch year | Why now |
| --- | --- | --- | --- | --- |
| 1 | SIGHT ID | Digital identity | 2027 | First dependency of everything else: reusable KYC and authentication across group products + third parties — the trust layer. |
| 2 | SIGHT PAY | Regional payment network | 2027 | Acquiring + cross-border rails connecting MNOs, banks and BTC liquidity. Monetises the existing BitLibera base immediately. |
| 3 | SIGHT ACADEMY | Talent institution | 2027 | Nothing scales without engineers and operators. Formalises LEARN BTC into the group's hiring pipeline from year one. |
| 4 | SIGHT SECURITY | Cybersecurity infra & SOC | 2028 | Payments and identity cannot run unprotected. Becomes a managed service sold to banks and public bodies. |
| 5 | SIGHT DATA | Data & analytics infra | 2028 | Group data platform once PAY and ID generate volume; commercial analytics for banks, MNOs, regulators. |
| 6 | SIGHT MEDIA | Media holding (AFJ + adjacencies) | 2028 | Cheap to stand up, compounds distribution and institutional credibility for every later launch. |
| 7 | SIGHT CLOUD | Sovereign cloud | 2029 | Local data residency for governments and regulated industries — required before any public-sector contract. |
| 8 | SIGHT GOV | Government services platform | 2029 | White-label civic stack: portals, payments, ID, records. Activated as soon as sovereign hosting exists. |
| 9 | SIGHT FOUNDATION | Public-interest arm | 2029 | Open-source, scholarships, civic tech. Protects the social license before the group becomes systemically visible. |
| 10 | SIGHT LABS | Applied R&D | 2030 | Cryptography, AI, hardware, civic tech — funded only once core products produce cash. |
| 11 | SIGHT CAPITAL | Venture arm + fund | 2030 | Backs adjacent founders, sources M&A, extends the ecosystem once the balance sheet allows it. |
| 12 | SIGHT MARKET | Digital commerce rails | 2031 | Catalog + checkout + logistics handoff for SME commerce, built on top of PAY and ID. |
| 13 | SIGHT COMPUTE | African GPU cloud | 2031 | AI sovereignty requires owned compute. Follows CLOUD and Yepo demand — otherwise we stay tenants forever. |
| 14 | SIGHT AGRI | Agricultural data & finance | 2032 | Combines DATA + PAY + COMPUTE for the continent's largest sector — needs all three to exist first. |
| 15 | SIGHT HEALTH | Health-data infrastructure | 2032 | Highest regulatory bar; launched last, on mature ID, CLOUD and SECURITY foundations. |

## 3. Phase priorities

| Phase | Years | Priority goals | Revenue | Funding |
| --- | --- | --- | --- | --- |
| Foundation | 2027 | Unify group identity · Stabilize MS + AFJ + Yepo + LEARN BTC · Establish governance | 15M FBU | Bootstrap + small angel (90M FBU) |
| Validation | 2028 | Repeatable revenue per product · Hire senior product/eng · Define group platform v0 | 60M FBU | Seed round 60–120M FBU (strategic angels + 1 African VC) |
| Growth | 2029–2030 | Launch sovereign infrastructure (CLOUD, GOV) · Open APIs · Open Kigali office | 220M → 600M FBU | Series A 300–450M FBU + DFI co-investment |
| Regional Expansion | 2031–2033 | Operate in 3+ countries · Government contracts · Sovereign cloud certifications | 1,5 → 5,5 Mds FBU | Series B/C 1,2–2,4 Mds FBU; blended capital with DFIs |
| Infrastructure Leadership | 2034–2036 | Foundational infra status · Public listing or strategic capital · African-owned compute | 9 → 18 Mds FBU | Pre-IPO / IPO / strategic minority partner |

## 4. Non-negotiable sequencing rules

- Nothing launches before its dependency exists: ID before PAY, PAY before MARKET, CLOUD before GOV.

- A new entity is created only when internal demand already covers at least half of its cost base.

- Cash-generating products keep priority over infrastructure ambitions in any given year.

- Maximum three new entities per year — beyond that, execution quality collapses.

- Every priority carries one owner, one deadline and one measurable indicator.